The following checklist should be considered as the minimum requirements for this position.  Note that some of the tasks are one-time actions; others are ongoing or repetitive for the duration of the incident. Tasks may be delegated to the appropriate Unit Leader

|  | ( |  | Task |
| --- | --- | --- | --- |
|  |  |  | Obtain briefing from Incident Commander: |
|  |  |  | Determine current resource status (ICS Form 201). |
|  |  |  | Determine current situation status/intelligence (ICS Form 201). |
|  |  |  | Determine current incident objectives and strategy. |
|  |  |  | Determine whether Incident Commander requires a written Incident Action Plan (IAP). |
|  |  |  | Determine time and location of first Planning Meeting. |
|  |  |  | Determine desired contingency plans. |
|  |  |  | Activate Planning Section positions, as necessary, and notify Resources Unit of positions activated. |
|  |  |  | Establish and maintain resource tracking system. |
|  |  |  | Complete ICS Form 201, if not previously completed, and provide copies to Command, Command Staff, and General Staff. |
|  |  |  | Advise Incident Command Post (ICP) staff of any significant changes in incident status. |
|  |  |  | Compile and display incident status summary information. Document on ICS Form 209, Incident Status Summary (or other approved agency forms): |
|  |  |  | Forward incident status summaries to Agency Administrator and/or other designated staff once per operational period, or as required. |
|  |  |  | Provide copy to Public Information Officer. |
|  |  |  | Obtain/develop incident maps. |
|  |  |  | Establish information requirements and reporting schedules for ICP and field staff. |

|  |  |  | Prepare contingency plans: |
| --- | --- | --- | --- |
|  |  |  | Review current and projected incident and resource status. |
|  |  |  | Develop alternative strategies. |
|  |  |  | Identify resources required to implement contingency plan. |
|  |  |  | Document alternatives for presentation to Incident Commander and Operations, and for inclusion in the written IAP. |
|  |  |  | Meet with Operations Section Chief and/or Command, prior to Planning Meetings, to discuss proposed strategy and tactics and diagram incident organization and resource location. |
|  |  |  | Conduct Planning Meetings according to following agenda: |
|  |  |  |  | Sample Planning Meeting Agenda |  |
|  |  |  |  | Agenda Item | Responsible Party |
|  |  |  | 1 | Briefing on situation/resource status. | Planning/Operations Section Chiefs |
|  |  |  | 2 | Discuss safety issues. | Safety Officer |
|  |  |  | 3 | Set/confirm incident objectives. | Incident Commander |
|  |  |  | 4 | Plot control lines & Division boundaries. | Operations Section Chief |
|  |  |  | 5 | Specify tactics for each Division/Group. | Operations Section Chief |
|  |  |  | 6 | Specify resources needed for each Division/Group. | Operations/Planning Section Chiefs |
|  |  |  | 7 | Specify facilities and reporting locations. | Operations/Planning/Logistics Section Chiefs |
|  |  |  | 8 | Develop resource order. | Logistics Section Chief |
|  |  |  | 9 | Consider communications/medical/ transportation plans. | Logistics/Planning Section Chiefs |
|  |  |  | 10 | Provide financial update. | Finance/Administration Section Chief |
|  |  |  | 11 | Discuss interagency liaison issues. | Liaison Officer |
|  |  |  | 12 | Discuss information issues. | Public Information Officer |
|  |  |  | 13 | Finalize/approve/implement plan. | Incident Commander/All |
|  |  |  | Supervise preparation and distribution of the written IAP, if indicated. Minimum distribution is to all Command, Command Staff, General Staff, and Operations personnel to the Division/Group Supervisor level: |
|  |  |  | Establish information requirements and reporting schedules for use in preparing the IAP. |
|  |  |  | Ensure that detailed contingency plan information is available for consideration by Operations and Command. |
|  |  |  | Verify that all support and resource needs are coordinated with Logistics Section prior to release of the IAP. |
|  |  |  | Include fiscal documentation forms in written IAP as requested by the Finance/Administration Section. |
|  |  |  | Coordinate IAP changes with General Staff personnel and distribute written changes, as appropriate. |
|  |  |  | Coordinate development of Incident Traffic Plan with Operations and the Ground Support Unit Leader. |
|  |  |  | Coordinate preparation of the Safety Message with Safety Officer. |
|  |  |  | Coordinate preparation of the Incident Communications Plan and Medical Plan with Logistics. |
|  |  |  | Instruct Planning Section Units in distribution of incident information. |
|  |  |  | Provide periodic predictions on incident potential. |
|  |  |  | Establish a weather data collection system, when necessary. |
|  |  |  | Identify need for specialized resources; discuss need with Operations and Command; facilitate resource requests with Logistics. |
|  |  |  | Ensure Section has adequate coverage and relief. |
|  |  |  | Hold Section meetings as necessary to ensure communication and coordination among Planning Section Units. |
|  |  |  | Ensure preparation of demobilization plan, if appropriate. |
|  |  |  | Ensure preparation of final incident package and route to Agency Administrator for archiving or follow-up after Incident Management Team (IMT) demobilization. |
|  |  |  | Provide briefing to relief on current and unusual situations. |
|  |  |  | Ensure that all staff observe established level of operational security. |
|  |  |  | Ensure all Planning functions are documenting actions on Unit Log (ICS Form 214). |
|  |  |  | Submit all Section documentation to Documentation Unit. |